## Tasks and Timeline
Sauce & Spoon - Tablet Rollout Project Plan
Task | Notes | Start Date | Due Date | Duration (days) | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Tablets received
Generate quotes and review costs |  | 2026-03-02 | 2026-03-04 | 3 | Project Manager | bar: WEEK 1 M to WEEK 1 W
Create SoW |  | 2026-03-05 | 2026-03-06 | 2 | Legal / Project Manager | bar: WEEK 1 R to WEEK 1 F
Order tablets & accesories |  | 2026-03-09 | 2026-03-12 | 3 | Procurement / PM | bar: WEEK 2 M to WEEK 2 W
Shipping and receiving tablets |  | 2026-03-11 | 2026-03-21 | 10 | Fulfillment Manager / IT | bar: WEEK 2 W to WEEK 4 W
Milestone: Restaurant renovated
Prepare contracts for electricians |  | 2026-03-11 | 2026-03-12 | 3 | IT / Facilities Lead | bar: WEEK 2 W to WEEK 2 F
Purchase wiring, electrical hardware, routers |  | 2026-03-15 | 2026-03-18 | 4 | Legal / Project Manager | bar: WEEK 3 T to WEEK 3 F
Bar tables wired up |  | 2026-03-28 | 2026-04-01 | 5 | Facilities Lead | bar: WEEK 5 M to WEEK 5 F
Milestone: Tablets configured and running
Design a customer satisfaction survey |  | 2026-03-23 | 2026-03-25 | 3 | Guest Experience Lead | bar: WEEK 4 M to WEEK 4 W
Design add-ons (coupons, promotions) | Wait for Carter to come up with the final menu | 2026-03-23 | 2026-03-26 | 4 | Marketing | bar: WEEK 4 M to WEEK 4 R
Load menues and features into the tablets | Wait for the add-ons to be completed | 2026-03-27 | 2026-03-31 | 5 | IT / Carter Ward | bar: WEEK 4 F to WEEK 5 R
Install an AI-based recommendation system |  | 2026-04-01 | 2026-04-01 | 1 | IT | bar: WEEK 5 F
Synchronize tablets software with current POS system |  | 2026-04-02 | 2026-04-04 | 3 | IT Lead | bar: WEEK 6 M to WEEK 6 W
Test functionality and optimize |  | 2026-04-05 | 2026-04-12 | 6 | QA Tester / IT | bar: WEEK 6 R to WEEK 7 R
Milestone: Training complete
Planning the "Train-the-trainer" model |  | 2026-03-28 | 2026-03-30 | 3 | HR | bar: WEEK 5 M to WEEK 5 W
Training key staff members (leads) |  | 2026-04-13 | 2026-04-14 | 2 | Seydou Diallo (Consultant) | bar: WEEK 7 M to WEEK 7 T
Peer-to-peer workshops to train the rest of the staff |  | 2026-04-20 | 2026-04-22 | 3 | Training Leads/ HR | bar: WEEK 8 M to WEEK 8 W
Document the staff feedback and post-training analysis |  | 2026-04-23 | 2026-04-27 | 3 | Project Manager | bar: WEEK 8 R to WEEK 9 M
Create SOPs and print manuals |  | 2026-04-27 | 2026-05-01 | 5 | Training Manager / HR | bar: WEEK 9 M to WEEK 9 F
Milestone: Marketing and branding done
Contact marketing department for branding and customization |  | 2026-03-02 | 2026-03-03 | 2 | Project Manager | bar: WEEK 1 M to WEEK 1 T
Upload branding to tablets |  | 2026-04-03 | 2026-04-04 | 2 | IT / Graphic Designer | bar: WEEK 5 F to WEEK 6 M
Promotion of the tablets by email/update social media |  | 2026-04-17 | 2026-05-01 | 10 | Social Media Manager | bar: WEEK 7 F to WEEK 9 F
Create signs and posters for the tabletop menu launch |  | 2026-04-20 | 2026-04-28 | 7 | Graphic Designer / Marketing | bar: WEEK 8 M to WEEK 9 T
Milestone: Launch Day complete
Create a launch day plan: special menu items, staffing, troubleshooting |  | 2026-05-03 | 2026-05-11 | 7 | Project Manager | bar: WEEK 10 M to WEEK 11 T
Map out pilot running areas and sitting spots |  | 2026-05-10 | 2026-05-12 | 3 | General Managers (Gilly/Alex) | bar: WEEK 11 M to WEEK 11 W
Inform & align stakeholders |  | 2026-05-14 | 2026-05-15 | 2 | Project Manager | bar: WEEK 11 R to WEEK 11 F
Test out the ordering system with staff & family |  |  | 2026-05-17 | 1 | All Staff (coordinated by PM) | bar: WEEK 11 F to WEEK 12 M
Refine operational protocols | Get approval by Deana | 2026-05-18 | 2026-05-21 | 3 | Operations Manager | bar: WEEK 12 M to WEEK 12 W
Launch day |  |  | 2026-05-23 | 1 | General Managers (Gilly/Alex) | bar: WEEK 12 F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Tablets received
Generate quotes and review costs |  | 2 | 5 hours | 1 day | 5 days | M
Create contracts and SoW for tablet vendors |  | 3 | 1 day | 2 days | 10 days | M
Order tablets & protective cases |  | 1 | 2 hours | 4 hours | 5 days | H
Shipping and receiving tablets |  | 10 | 5 days | 7 days | 30 days | H
Milestone: Restaurant adapted and running
Purchase wiring, electrical hardware, routers |  | 3 | 1 day | 2 days | 5 days | H
Prepare contracts for electricians |  | 2 | 5 hours | 1 day | 5 days | H
Bar tables wired up |  | 5 | 2 days | 4 days | 10 days | L
Milestone: Tablets configured and running
Design add-ons (coupons, promotions) | Wait for Carter to come up with the final menu | 4 | 1 day | 3 day | 4 days | L
Design a customer satisfaction survey |  | 5 | 3 days | 1 day | 6 days | M
Load menues and features into the tablets | Wait for the add-ons to be completed | 5 | 2 hours | 1 week | 2 weeks | L
Install an AI-based recommendation system |  | 1 | 2 hours | 1 day | 5 days | M
Synchronize tablets software with current POS system |  | 3 | 2 hours | 2 days | 5 days | L
Test functionality and optimize |  | 5 | 2 days | 3 days | 7 days | M
Milestone: Training complete
Planning of "Train-the-trainer" model |  | 3 | 2 days | 3 days | 5 days
Designated leads for first-round training |  | 2 | 1 day | 2 days | 5 days | H
Peer-to-peer workshops to train the rest of the staff |  | 2 | 1 day | 2 days | 5 days | H
Document the staff feedback and post-training analysis |  | 3 | 2 days | 3 days | 6 days | H
Create SOPs and print manuals |  | 5 | 2 days | 4 days | 10 days | M
Milestone: Marketing and branding done
Contact marketing department for branding and customization |  | 2 | 6 hours | 1 day | 5 days | H
Upload branding to tablets |  | 1 | 2 hours | 1 day | 5 days | H
Promotion of the pilot rollout by email/update social media |  | 7 | 3 days | 5 days | 10 days | M
Create signs and posters for the tabletop menu launch |  | 10 | 5 | 7 | 20 | M
Milestone: Launch Day complete
Create a launch day plan: special menu items, staffing, troubleshooting |  | 7 | 3 | 5 | 10 | M
Map out pilot running areas and sitting spots |  | 3 | 1 day | 2 days | 5 days | M
Inform & align stakeholders |  | 2 | 6 hours | 1 day | 1 week | H
Test out the ordering system with staff & family |  | 2 | 4 hours | 1 day | 5 days | H
Refine operational protocols |  | 3 | 1 day | 2 days | 10 days | M
Launch day |  | 2 | 1 day | 2 days | 1 week | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
The success formula for restaurants in 2026: 5 digital tips to boost profitability | https://www.finedinemenu.com/en/blog/the-success-formula-for-restaurants-in-2026-5-digital-tips-to-boost-profitability/ | 2026-01-07
Restaurant Tablet Best Practices: Smart Strategies For Success | https://get.chownow.com/blog/restaurant-tablet-best-practices/ | 2026-01-07
Restaurants Tablets best practices, what's the industry standard | https://solink.com/resources/industry-insights/restaurant-tablet-best-practices/ | 2026-01-07
Best tips for using a Restaurant Tablet ordering system | https://themelooks.com/best-tips-for-using-a-restaurant-tablet-ordering-system/#:~:text=run%20more%20smoothly.-,Keep%20the%20Tablet%20Menu%20Fresh%20and%20Attractive,customers%20choose%20what%20they%20like. | 2026-01-07

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction | 10% increase in appetizer ordering | What are the most common menu items ordered? | Dishes ordered | FALSE
Customer satisfaction | average ticket time of 8 min for appetizers and 12-15 min for entrees | How can we improve service times? | Ticketing time | FALSE
Customer satisfaction | one-minute checkout time | What are the costs and benefits of using multiple payment options? | Use of tablet for check out, satisfaction survey | FALSE
Customer satisfaction | less than 5% of customers to report technical issues | Were there unintended outcomes? | Technical reports | FALSE
Customer satisfaction | 98% order accuracy | Are we meeting our goals? | Sent-back orders, cancelled orders | FALSE
Customer satisfaction | Lobby average wait time of under ten minutes | How can we improve waiting times? | Table turn times, lobby wait time | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
10% increase in appetizer ordering | What are the most common menu items ordered? | Type of dishes ordered | During your visit, what did you order? Choose all that apply | Multiple choice | Appetizers | Entrees | Dessert | Drinks
average ticket time of 8 min for appetizers and 12-15 min for entrees | How can we improve our ticketing time? | Ticketing time | Approximately, how long did you wait for your order to arrive? | Multiple choice | Less than 8 min | 8-10 min | 15-20 min | more than 20 min
|  | Ticketing time | Did you order multiple items? In that case, did they arrive at similar times? | Yes/No
one-minute checkout time | What are the costs and benefits of using integrated payment on the tablets? | Use of tablet for check out | Did you use the tablet system for checking out? | Yes/No
one-minute checkout time | Should we continue using the tablet for checkout? | Satisfaction survey | How easy was to use the tablet navigation? | Scaled | Difficult | Slightly difficult | Neutral | Somewhat easy | Easy
one-minute checkout time | Should we continue using the tablet for checkout? | Satisfaction survey | On a scale of one to five, how would you rate the tablet checkout process versus a standard service? | Scaled | 1 = Very slow | 2 = Somewhat slow | 3 = neutral | 4 = Somewhat fast | 5 = Very fast
less than 5% of customers to report technical issues | Were there unintended outcomes? | Technical reports | Did you encounter any technical issues or other erros during ordering? | Yes/No
less than 5% of customers to report technical issues |  | Technical reports | On a scale of one to five, how satisfied were you with the tablet performance? | Scaled | 1 = Unsatisfied | 2 = Somewhat dissatisfied | 3 = Neither satisfied nor unsatisfied | 4 = Somewhat satisfied | 5 = Very satisfied
less than 5% of customers to report technical issues |  | Technical reports | In your words, can you describe any issues you faced when using the tablet? | Open-ended
98% customers receive the right order | Are we meeting our goals? | Sent-back orders, cancelled orders | Your order met your expectations and every ingredient was specified and/or modified to your preference | True/False
|  | Sent-back orders, cancelled orders | Did you return any item ordered through the tablet? If so, describe the issue | Multiple choice | no returns | received the wrong item(s) | returned items that did not match the description | returned misprepared items or with incorrect ingredients | other issue (please specify)
Lobby average wait time of under ten minutes | How can we improve waiting times? | Table turn times, lobby wait time | How can we improve waiting times before sitting? | Open-ended
Lobby average wait time of under ten minutes |  |  | How long did you wait to be seated? | Multiple choice | Between 5 to 10 min | Between 10 to 15 min | More than 20 min