## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Project team | Went well | all tablets installed and working | Gilly and Alex comments
Customers | Needs improvement | Table turn times | Survey data | look at sent-back orders
Customers | Needs improvement | Sent back orders | data points
Project team | Went well | Ticket flow | Zane and Larissa comments
Project team | Went well | Fixed technical issues in POS integration system | Seydou comments | Update the process manual
Project team | Needs improvement | Not enough participants in birthday program | Seydou comments | designer to update website content to clarify the program
Project team | Went well | weekly calls with vendors | Peta comments | make sure to keep the cadence
Project team | Went well | Met most of customer satisfaction standards | Peta comments, survey data
Project team | Needs improvement | Unplanned operational issues | Peta comments | understanding each location's history
Project team | Needs improvement | capacity and people available - risk management | Seydou comments | plan things properly to avoid last time adjustments
Project team | Needs improvement | scale up operations in BOH | Zane comments
Project team | Needs improvement | FOH and BOH communication | Larissa comments | share experiences
Project team | Needs improvement | Waitstaff training process | Alex comments | Comprehensinve training - make two days instead of one
Customers | Went well | Overall experience with tablets | survey data
Customers | Went well | Checkout process | survey data | Include solutions for people that pay with cash
Customers | Needs improvement | Usability of tablets to order | survey data | Improve interface design