## Dashboard
Project Name: Plant Pals Operations & Training
Description: This document centralizes important information for the Project planning and execution phases
Owner: Josefina H
Status: Draft/Active/Inactive
Key Docs | Description
Project charter | A formal short document providing managers with authority to begin with Operations and Training plan
Statement of work | Legally binding document with the vendors for activities related to this project/part of this project
Risk management plan | A document destined to prevent and mitigate risks associated with the proejct
Schedule | Identifies timelines and due dates for each task and the responsibles associated with them
Budget | A calculation document for planned expenses and estimated total cost for the project along with under and over runs
Communication plan | Organizes how and when the information related to the project should be shared with stakeholders
Shared folder | Folder with relevant documentation
RACI chart | A responsibility assignment matrix that clarifies roles and responsibilities within the project team

## Project Schedule
PROJECT MANAGER: Josefina H | [6 empty] | CREATION DATE: |  |  |  |  | 2025-02-05
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Establish a plant delivery and logistics plan | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 10 | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Hire delivery drivers | HR Specialist | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | calculate delivery fees | Financial Analyst | 3/29 | 4/2 | 5 | 0% | bar: MARCH M 29 to APRIL F 2
2 | Select and install supply chain software and equipment
2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory Manager | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Supervise vendor installation of the fulfillment equipment | Fulfillment Director | 3/30 | 4/8 | 8 | 0% | bar: MARCH T 30 to APRIL R 8
2.3 | Establish internal safery protocols for equipment | Quality Assurance Tester | 4/19 | 4/30 | 10 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Develop and launch an employee training program
3.1 | Develop training sessions | HR Specialist | 5/3 | 5/13 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Train employees to use the software and equipment | Training Manager | 5/18 | 5/28 | 10 | 0% | bar: MAY T 18 to MAY F 28
3.3 | Monitor progress and improve traninig processes | Training Manager | 5/19 | 6/8 | 15 | 0% | bar: MAY W 19 to JUNE T 8

## Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 62000 | 0 | 62000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Purchase delivery trucks |  |  |  | 2 | 15000 |  | 30000 |  | -30000
Task 2: Source packaging materials |  |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3: Pay delivery drivers | Delivery Driver (2) | 160 | 15 |  |  |  | 2400 |  | -2400
-- | [5 empty] | Total | 35400 | 0
Milestone 2: Select and install supply chain management software and equipment
Task 1: Source vendor (includes setup, installation, and deployment of software and equipment systems) | [5 empty] | 15000 | 15000 |  | -15000
-- | [5 empty] | Total | 15000 | 0
Milestone 3: Develop and launch an employee training program
Task 1: Develop training sessions | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2: Train employees to use the software and equipment | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
Task 3: Monitor employee progress and improve training processes | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
-- | [5 empty] | Total | 8000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 62000 | 0

## Communication Plan
Project Plant Pals: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings.
Software and Equipment Vendor | Planning Meeting | Weekly | Project Manager | Tuesday 10 AM | In Person | Go over the training manual in order to create an effective training plan for Office Green's employees
Human Resources | Planning Meeting | Weekly | Core Team: Training Manager | Each Monday at 11 AM | Email (from company address) | Project planning assistance; provide support during the training session
Facilities | Planning Check-In | One time | Core Team: Administrative Coordinator | 8th day | Phone Call | Reserve rooms, spaces, and equipment needed for employee training | Meeting Room schedule spreadsheet
Print Shop | Planning Check-In | One time | Core Team: Administrative Coordinator | 5th day | Phone Call | Coordinate on the printing and delivery of training manuals for employees | Vendor website & phone number
Office Green employees | Informational Update | One time | Core Team: HR Specialist | 6th day | In Person | Communicate schedules, locations, and other necessary details to trainees
Office Green employees | Training | One time | Core Team: Training Manager | 10th day (launch) | In Person | Train employees to use the supply chain management software and equipment |  | Plan extra day for unexpected cancellations/ abscences
Office Green employees | Survey | One time | Core Team: Training Manager | 11th day | Email (from company address) | Post-training survey
Your Manager | Status Update | Weekly | Project Manager | every Monday at 2 PM | Email (from company address) | Update on event planning, ask questions, and get feedback
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | One time | Project Manager | 8th day | In Person | High-level information and general updates